## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PRJ_HMS
Project Name | Hotel Management System
Prepared/Modified by | Role | Date of Preparation
Ijas Ahamed | Tester | 2018-10-05
Reviewed by | Role | Date of Review
Himanshu ,Kartik , Harsitha | SME
Approved by | Role | Date of Approval
Christy Henitha | Test Manager
Circulation List
Version Number | 1

## Registration
Project ID: PRJ_HMS |  | Project Name : Hotel Management System
Defect Id. | Module name | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_REGISTRATION_001 |  | Registration | The User id field in the Registration page is found to accept special characters. | Detailed Description: The User id field in the Registration page is found to accept special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter User Id(using special characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts special characters in the User id field .The application proceeds to the next page. There is no error message shown as expected. | Coding | chrome | Internal Dev | High | Medium | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_002 |  | Registration | The Password field in the Registration page is unable to accept special characters. | Detailed Description: The Password field in the Registration page is unable to accept special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter password(using special characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but cannot accept special characters in the Password field . The application proceeds to the next page without popping any error message. | Coding | chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_003 |  | Registration | The Password field in the Registration page is unable to accept more than 10 characters. | Detailed Description: The Password field in the Registration page is unable to accept more than 10 characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter password(using more than 10 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but cannot accept more than 10 characters in the Password field .The application proceeds to the next page without popping any error message. | Coding | chrome | Internal Dev | Medium | Medium | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_004 |  | Registration | The Username field in the Registration page accepts special characters and numbers. | Detailed Description: The Username field in the Registration page accepts special characters and numbers. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Username(using special characters and numbers) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields and accepts special characters and numbers in the Username field .The application proceeds to the next page without popping any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_005 |  | Registration | The Username field in the Registration page accepts name with 1 character. | Detailed Description: The Username field in the Registration page accepts name with 1 character. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Username(using only 1 character) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept only 1 character in the Username field .The application proceeds to the next page without popping any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_006 |  | Registration | The mobile number field in the Registration page accepts more than 10 numbers. | Detailed Description: The mobile number field in them Registration page accepts more than 10 digits. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter mobile number(using more than 10 digits) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept more than 10 digits in the mobile number field .The application proceeds to the next page. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_007 |  | Registration | The mobile number field in the Registration page accepts less than 10 numbers. | Detailed Description: The mobile number field in the Registration page accepts less than 10 digits. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter mobile number(using less than 10 digits) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept less than 10 digits in the mobile number field .The application proceeds to the next page without popping any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_008 |  | Registration | The mobile number field in the Registration page accepts alphabets and special characters. | Detailed Description: The mobile number field in the Registration page accepts alphabets and special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter mobile number(using alphabets and special characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept alphabets and special characters in the mobile number field .The application proceeds to the next page without popping any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_009 |  | Registration | The mobile number field in the Registration page is accepting mobile number beginning between 0-5 instead Indian mobile numbers should begin with 6 or 7 or 8 or 9 . | Detailed Description: The mobile number field in the Registration page accepts mobile numbers beginning with 0-5. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter mobile number(using any number between 0-5 in the beginning) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept mobile number beginning with 0-5 in the mobile number field .The application proceeds to the next page without popping any error message regarding mobile number. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_010 |  | Registration | The phone\alternate number field in the Registration page accepts more than 10 numbers. | Detailed Description: The phone\alternate number field in the Registration page accepts more than 10 digits. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter phone\alternate number(using more than 10 digits) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept more than 10 digits in the phone\alternate number field . The application proceeds to the next page without popping any error message | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_011 |  | Registration | The phone\alternate number field in the Registration page accepts less than 10 numbers. | Detailed Description: The phone\alternate number field in the Registration page accepts less than 10 digits. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter phone\alternate number(using less than 10 digits) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept less than 10 digits in the phone\alternate number field .The application proceeds to the next page without popping any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_012 |  | Registration | The phone\alternate number field in the Registration page accepts alphabets and special characters. | Detailed Description: The phone\alternate number field in the Registration page accepts alphabets and special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter phone\alternate number(using alphabets and special characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept alphabets and special characters in the phone\alternate number field .The application proceeds to the next page without popping any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_013 |  | Registration | The phone\alternate number field in the Registration page is accepting phone\alternate number beginning between 0-5 instead Indian phone\alternate numbers should begin with 6 or 7 or 8 or 9 . | Detailed Description: The phone\alternate number field in the Registration page accepts mobile numbers beginning with 0-5. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter phone\alternate number(using any number between 0-5 in the beginning) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept phone\alternate number beginning with 0-5 in the phone\alternate number field .The application proceeds to the next page without popping any error message regarding mobile number. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_014 |  | Registration | The phone\alternate number field in the Registration page is accepting number which is already entered in mobile number field . | Detailed Description: The phone\alternate number field in the Registration page is accepting number which is already entered in mobile number field but mobile number and alternate number should not match. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter phone\alternate number(same as mobile number) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and it is also accepting alternate phone number as same as mobile number.The application proceeds to the next page with blindly accepting the altenate number without popping up message regarding the matching of alternate number. | Coding | chrome | Internal Dev | low | medium | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_015 |  | Registration | The e-mail field in the Registration page is accepting numbers in local-part of e-mail . Eg :123456@gmai.com | Detailed Description: The e-mail field in the Registration page accepts numbers in local-part of the e-mail. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter e-mail(using 123456@gmail.com) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept numbers in local-part of e-mail field. The application proceeds to the next page without popping any error message regarding e-mail. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_016 |  | Registration | The e-mail field in the Registration page is accepting e-mail id without server name. Eg : someone@gmal | Detailed Description: The e-mail field in the Registration page accepting e-mail id without server name. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter e-mail(using someone@gmail) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept e-mail id without server name.The application proceeds to the next page without popping any error message regarding e-mail id . | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_017 |  | Registration | The e-mail field in the Registration page is accepting e-mail id without domain name. Eg : someone@.com | Detailed Description: The e-mail field in the Registration page accepting e-mail id without domain name. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter e-mail(using someone@.com) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accept e-mail id without domain name. The application proceeds to the next page without popping any error message regarding e-mail id . | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_018 |  | Registration | The address field in the Registration page is accepting address from 1 characters.(Minimum limit is not set) Eg : c (not a complete address) | Detailed Description: The address field in the Registration page accepting address from 1 characters (Minimum limit is not set). Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter addressl(using c) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accepts address from 1 to many characters (Minimum limit is not set). The application proceeds to the next page without popping any error message regarding address. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_019 |  | Registration | The address field in the Registration page is accepting numbers as address. Eg : 123456 (not a complete address) | Detailed Description: The address field in the Registration page accepting numbers as address . Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter addressl(using 123456) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and can also accepts numbers as address. The application proceeds to the next page without popping any error message regarding address. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_020 |  | Registration | The address field in the Registration page is not marked as mandatory. Eg : address : | Detailed Description: The address field in the Registration page does not show error message when address is left blank. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Leave address blank 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in the other credential fields and does not show any error message when address is left blank (address is not markes as mandatory). The application proceeds to the next page without popping any error message regarding address. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_021 |  | Registration | The SUBMIT button in the Registration page is not registering the new user even if the details entered by the new user are valid. | Detailed Description: The SUBMIT button in the Registration page is not registering the new user even if the details entered by the new user are valid. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Valid credentials 5. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept valid values in all credential fields but cannot register new user when submit button is clicked. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_REGISTRATION_022 |  | Registration | The RESET button in the Registration page is not resetting\clearing the fields in the page when the reset button is clicked. | Detailed Description: The RESET button in the Registration page is not resetting\clearing the fields in the page when the reset button is clicked . Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Valid credentials 5. Click on reset button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept values in all credential fields but cannot reset\clear data present in the fields when reset button is clicked. | Coding | chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Give the name of the module being tested
Note on D3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on E3: Alphy Chenganiyadan: A detailed description of the defect
Note on F3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on G3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on H3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on I3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on J3: Prioritize the defect
Note on K3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on M3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on N3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on O3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on P3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on Q3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on R3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on S3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on T3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on U3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on V3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on W3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on Y3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Z3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Login
Project ID: PRJ_HMS | Project Name : Hotel Management System
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_LOGIN_001 | Login Page | The Username field in the Login page is found to accept numbers and special characters. | Detailed Description: The Username field in the Login page is found to accept numbers and special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Enter Username(using numbers and special characters) 5. Enter password. 6. Click on Login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts password in the password fields and also accepts numbers and special characters in the Username field. The application proceeds to the next page.There is no error message shown for username as expected. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_LOGIN_002 | Login Page | The Password field in the Login page is unable to accept numbers and special characters . | Detailed Description: The Password field in the Login page is unable to accept numbers and special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Enter Username. 5. Enter Password (using numbers and special characters). 6. Click on Login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts username in the username fields and cannot accept numbers and special characters in the password field. The application is not responding accordingly as it cannot accept number and special characters. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_LOGIN_003 | Login Page | The Login button in the Login page is unable to verify for the existence of username in the database . | Detailed Description: The Login button in the Login page is unable to verify for the existence of username in the database. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Enter Username. 5. Enter Password . 6. Click on Login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts username and password but it cannot verify for the existence of username in the database when login button is clicked. The application is not displaying the login status when login button is clicked. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_LOGIN_004 | Login Page | The Login button in the Login page is unable to verify for the matching of password with the username entered by the user. | Detailed Description: The Login button in the Login page is unable to verify for the existence of username in the database. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Enter Username. 5. Enter Password . 6. Click on Login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts username and password but it cannot verify for the existence of usename in the database when login button is clicked. The application is not displaying the login status when login button is clicked. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_LOGIN_005 | Login Page | The Signup link in the Login page is unable to display the signup\register page for signning up new user. | Detailed Description: The Signup link in the Login page is unable to display the signup\register page for signning up new user. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Click on signup link. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to display the signup\register page when signup link is clicked. The application is not displaying the signup\register when signup link is clicked. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Search By City
Project ID: PRJ_HMS | Project Name : Hotel Management System
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_SEARCH_BY_CITY_001 | Search by city | The select city field in the search by city page is only able to select Mumbai city , no other city is included in drop down. | Detailed Description: The select city field in the search by city page is only able to select Mumbai city. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5. Select drop down option for selecting city. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept only Mumbai in the select city box , no other city is included in drop down list. So user can only select Mumbai irrespective of which city they search for. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_002 | Search by city | The select city field in the search by city page is selecting Mumbai city by default, if the user forgets to select the city name. | Detailed Description: The select city field in the search by city page is selecting Mumbai city by default , when the uuser forgets to select the city from drop down of the select city. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Select details for all fields except select city. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all other fields and by default selects Mumbai for the select city box when the user forgets to select city name from select city drop down. So user will get details of Mumbai by default irrespective of which city they search for. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_003 | Search by city | The arrival date field in the search by city page is able to accept date 30,31 for the month february. | Detailed Description: The arrival date field in the search by city page is able to accept date 30,31 for the month february. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter date 30 or 31 for the month february. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all other fields and it also accepts date 30 and 31 for the month february. No details of the room is displayed as the date is invalid but no error message for the invalid date is also displayed. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_004 | Search by city | The arrival date field in the search by city page is able to accept date 31 for the months april , june , september , november. | Detailed Description: The arrival date field in the search by city page is able to date 31 for the months april , june , september , november. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter date 31 for any of these months(april , june , september , november) . Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all other fields and it also accepts date 31 for the following months (april , june , september , november). No details of the room is displayed as the date is invalid but no error message for the invalid date is also displayed. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_005 | Search by city | The arrival date field in the search by city page is able to accept date 29 for the month february, even if it is not a leap year. | Detailed Description: The arrival date field in the search by city page is able to date 29 for the month february even if it is not a leap year. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter date 29 for the month february where year is not a leap year. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all other fields and it also accepts date 29 for the month february even if the year is not a leap year. No details of the room is displayed as the date is invalid but no error message for the invalid date is also displayed. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_006 | Search by city | The arrival date field in the search by city page is able to accept date which is less than system date. (arrival date less than current date is impossible) | Detailed Description: The arrival date field in the search by city page is able to accept date which is less than current date. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter date which is less than current\today's date. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all other fields and it also accepts date which is less than current date but it is impossible to arrive in a date which is passed. No details of the room is displayed as the date is invalid but no error message for the invalid date is also displayed. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_007 | Search by city | The departure date field in the search by city page is able to accept date which is less than system date.( Departure is impossible in a date which is already passed ) | Detailed Description: The departure date field in the search by city page is able to accept date which is less than system date .( Departure is impossible in a date which is already passed ). Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter departure date which is less than current\today's date . Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all other fields and it also accepts date which is less than current date but it is impossible to arrive in a date which is passed. No details of the room is displayed as the date is invalid but no error message for the invalid date is also displayed. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_008 | Search by city | The departure date field in the search by city page is able to accept date which is less than arrival date.( Departure date can be equal to arrival date but not less than arrival date ) | Detailed Description: The departure date field in the search by city page is able to accept date which is less than arrival date . (Departure date can be less than arrival date but not less than arrival date). Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter departure date which is less than arrival date . Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all other fields and it also accepts date which is less than arrival date but it is impossible to deaprt before arrival. No details of the room is displayed as the date is invalid but no error message for the invalid date is also displayed. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_009 | Search by city | The search button in the search by city page is unable to validate city , arrival date and departure date and display the result.(search button is not functioning as expexted) | Detailed Description: The search button in the search by city page is unable to validate city , arrival date and departure date and display the result. (search button is not functioning as expexted) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter valid values in all fields . 6.Click search button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all fields but it cannot able to validate city , arrival date and departure date and display the result. No details of the room is displayed as the search button is not functioning as expected. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_0010 | Search by city | The search button in the search by city page is only able to validate city , arrival date and displaying the result.(search button is not considering departure date) | Detailed Description: The search button in the search by city page is only able to validate city , arrival date and displaying the result.(search button is not considering departure date) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter valid values in all fields . 6.Click search button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all fields but it can only able to validate city , arrival date and displaying the result. Details of the room is displayed considering city and arrival date as search button is unable to consider departure date. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_011 | Search by city | The search button in the search by city page is only able to validate city , departure date and displaying the result.(search button is not considering arrival date) | Detailed Description: The search button in the search by city page is only able to validate city , departure date and displaying the result.(search button is not considering arrival date) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter valid values in all fields . 6.Click search button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all fields but it can only able to validate city , departure date and displaying the result. Details of the room is displayed considering city and departure date as search button is unable to consider arrival date. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_012 | Search by city | The search button in the search by city page is only able to validate arrival date , departure date and displaying the result.(search button is not considering city) | Detailed Description: The search button in the search by city page is only able to validate arrival date , departure date and displaying the result.(search button is not considering city). Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter valid values in all fields . 6.Click search button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all fields but it can only able to validate arrival date , departure date and displaying the result. Details of the room is displayed considering arrival date and departure date as ,search button is unable to consider city. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_013 | Search by city | The search button in the search by city page is only able to validate arrival date and displaying the result.(search button is not considering city and departure date) | Detailed Description: The search button in the search by city page is only able to validate arrival date and displaying the result.(search button is not considering city and departure date). Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter valid values in all fields . 6.Click search button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all fields but it can only able to validate arrival date and displaying the result. Details of the room is displayed considering arrival date as search button is unable to consider city and departure date. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_014 | Search by city | The search button in the search by city page is only able to validate city and displaying the result.(search button is not considering arrival date and departure date) | Detailed Description: The search button in the search by city page is only able to validate city and displaying the result.(search button is not considering arrival date and departure date). Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter valid values in all fields . 6.Click search button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all fields but it can only able to validate city and display the result. Details of the room is displayed considering city as search button is unable to consider arrival date and departure date. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_SEARCH_BY_CITY_015 | Search by city | The search button in the search by city page is only able to validate departure date and displaying the result.(search button is not considering arrival date and city) | Detailed Description: The search button in the search by city page is only able to validate departure date and displaying the result.(search button is not considering arrival date and city). Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select search by city option from the page 5.Enter valid values in all fields . 6.Click search button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details in all fields but it can only able to validate departure date and display the result. Details of the room is displayed considering departure date as search button is unable to consider arrival date and city. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Book Now
Project ID: PRJ_HMS | Project Name : Hotel Management System
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_BOOK NOW_001 | BOOK NOW | The number of rooms field in the book now page is able to accept number greater than rooms available in that particular hotel\category. | Detailed Description: The number of rooms field in the book now page is able to accept number greater than rooms available in that particular hotel\category. (number of rooms to be booked must not be greater than available number of rooms but it can be equal ) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select book now option from the page 5. Enter a number greater than the number present in available number of rooms. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept number greater than the number that is present in available number of rooms. The user cannot book rooms greater than the availability of rooms in that particular hotel\category | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_BOOK NOW_002 | BOOK NOW | The number of rooms field in the book now page is able to accept number greater than rooms available in that particular hotel\category. | Detailed Description: The number of rooms field in the book now page is able to accept number greater than rooms available in that particular hotel\category. (number of rooms to be booked must not be greater than available number of rooms but it can be equal ) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select book now option from the page 5. Enter a number greater than the number present in available number of rooms. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept number greater than the number that is present in available number of rooms. The user cannot book rooms greater than the availability of rooms in that particular hotel\category | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_BOOK NOW_003 | BOOK NOW | The no of adults field in the add new hotel page is able to accept more than 2 adults per room .( LIMIT : max (2 adults +1 child) / room) | Detailed Description: The no of adults field in the add new hotel page is able to accept kore than 2 adults. ( LIMIT : max (2 adults +1 child) / room) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter no of adults with any number greater than 2. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept no of adults with more than 2 adults/Per. ( LIMIT : 2 adults +1 child / room) No of adults must not be greater than 2/room.It is accepting the invalid entry without displaying error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_BOOK NOW_004 | BOOK NOW | The no of child field in the add new hotel page is able to accept more than 1 child per room . ( LIMIT : max (2 adults +1 child) / room) | Detailed Description: The no of child field in the add new hotel page is able to accept more than 1 child. ( LIMIT : max (2 adults +1 child) / room) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter no of child greater than 1 . Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept no of child with more than 1 child/room. ( LIMIT : max (2 adults +1 child) / room) . No of child can only be equal to 1/room.It is accepting the invalid entry without displaying error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Add New Hotel
Project ID: PRJ_HMS | Project Name : Hotel Management System
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_ADD_NEW_HOTEL_001 | ADD NEW HOTEL | The enter hotel city field in the add new hotel page is able to accept numbers and special characters. | Detailed Description: The enter hotel city field in the add new hotel page is able to accept numbers and special character city name should have only alphabets Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter city name using numbers and special characters. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept number and special characters in the enter city name field. City name must not be in the form of numbers and special characters.No error message is displayed and the city name is accepted. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_002 | ADD NEW HOTEL | The enter hotel name field in the add new hotel page is not getting validated when it is left blank. | Detailed Description: The enter hotel name field in the add new hotel page is not getting validated when it is left blank. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Leave hotel name blank and enter other valid fields. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details without hotel name. Hotel name must not be left blank while adding a new hotel in the website.No error message is displayed and the New hotel details is accepted and registered. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_003 | ADD NEW HOTEL | The enter address field in the add new hotel page is not accepting address with more than 20 characters. | Detailed Description: The enter address field in the add new hotel page is not accepting address more than 20 characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter address with more than 20 characters. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application cannot accept address with more than 20 characters. Hotel address may exceed more than 20 characters.Only first 20 characters of the address is registered without any pop-ups. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_004 | ADD NEW HOTEL | The average fare per night field in the add new hotel page is accepting alphabets and special characters. | Detailed Description: The average fare per night field in the add new hotel page is accepting alphabets and special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter average fare per night with alphabets and special characters. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept alphabets and special characters in average fare per night field. Average fare per night should not accept alphabets and special characters.No error message is displayed and the invalid entry is registered. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_005 | ADD NEW HOTEL | The phone number 1 field in the add new hotel page is accepting alphabets and special characters and 10 digit validation is not done. | Detailed Description: The phone number 1 field in the add new hotel page is accepting alphabets and special characters and 10 digit validation is not done. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter phone number 1 with alphabets and special characters. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept phone number 1 with alphabets and special characters. Phone number 1 should not accept alphabets and special characters and should be equal to 10 digits.It is accepted without any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_006 | ADD NEW HOTEL | The phone number 2 field in the add new hotel page is accepting the same number which is entered in phone number 1 . (phone number 1 and phone number 2 should not be the same) | Detailed Description: The phone number 2 field in the add new hotel page is accepting the same number which is entered in phone number 1. (phone number 1 and phone number 2 should not be the same) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter phone number 2 as same as phone number 1. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept phone number 2 as same as phone number 1. Phone number 2 should not be as same as phone number 1.It is accepted without any acknowledgement. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_007 | ADD NEW HOTEL | The rating field in the add new hotel page has no values in the drop-down. (select is registered by default) | Detailed Description: The rating field in the add new hotel page has no values in the drop-down. (select is registered by default) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Click rating drop-down and check for the rating values. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is registering select in the rating drop down by default. Rating should have some values.It is accepted without any acknowledgement. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_008 | ADD NEW HOTEL | The e-mail field in the add new hotel page is not validating the e-mail for the local-name , domain and extension. ("locat-name@domain.extension" format is not getting verified) | Detailed Description: The e-mail field in the add new hotel page is not validating the e-mail for the local-name , domain and extension. ("locat-name@domain.extension" format is not getting verified) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter e-mail address without any proper e-mail format. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is accepting invalid e-mail address. E-mail should be in proper format.It is accepted without any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_09 | ADD NEW HOTEL | The fax field in the add new hotel page is not registering the fax number in the hotel page after registration. | Detailed Description: The fax field in the add new hotel page is not getting registered and displayed in that hotel page after regiatering. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter fax number. 6. Click on add hotel. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is accepting valid data in all fields , but after adding hotel , it is unable to display the fax number of that particular hotel. Fax number must be available in the web page of that particular hotel. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_10 | ADD NEW HOTEL | The Add hotel button in the add new hotel webpage is unable to add the new hotel details when it is clicked. | Detailed Description: The Add hotel button in the add new hotel webpage is unable to add the new hotel details when it is clicked. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter valid details in all fields. 6. Click on add hotel. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is accepting valid data in all fields , but the webpage is unable to add the details of the new hotel in the database. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_ADD_NEW_HOTEL_10 | ADD NEW HOTEL | The reset button in the add new hotel webpage is unable to reset the details in the fields when it is clicked. | Detailed Description: The reset button in the add new hotel webpage is unable to reset the details in the fields when it is clicked. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select add new hotel option from the page 5. Enter details in fields. 6. Click on reset. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to reset\clear the details in the fields when it is clicked. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Update New Hotel
Project ID: PRJ_HMS | Project Name : Hotel Management System
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_UPDATE_HOTEL_001 | UPDATE_HOTEL | The enter hotel city field in the update hotel page is able to accept numbers and special characters. | Detailed Description: The enter hotel city field in the update hotel page is able to accept numbers and special character city name should have only alphabets Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter city name using numbers and special characters. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept number and special characters in the enter city name field. City name must not be in the form of numbers and special characters. No error message is displayed and the city name is accepted. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_002 | UPDATE_HOTEL | The enter hotel name field in the update hotel page is not getting validated when it is left blank. | Detailed Description: The enter hotel name field in the update hotel page is not getting validated when it is left blank. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Leave hotel name blank and enter other valid fields. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept details without hotel name. Hotel name must not be left blank while adding a new hotel in the website. No error message is displayed and the New hotel details is accepted and registered. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_003 | UPDATE_HOTEL | The enter address field in the update hotel page is not accepting address with more than 20 characters. | Detailed Description: The enter address field in the update hotel page is not accepting address more than 20 characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter address with more than 20 characters. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application cannot accept address with more than 20 characters. Hotel address may exceed more than 20 characters. Only first 20 characters of the address is registered without any pop-ups. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_004 | UPDATE_HOTEL | The average fare per night field in the update hotel page is accepting alphabets and special characters. | Detailed Description: The average fare per night field in the update hotel page is accepting alphabets and special characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter average fare per night with alphabets and special characters. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept alphabets and special characters in average fare per night field. Average fare per night should not accept alphabets and special characters. No error message is displayed and the invalid entry is registered. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_005 | UPDATE_HOTEL | The phone number 1 field in the update hotel page is accepting alphabets and special characters and 10 digit validation is not done. | Detailed Description: The phone number 1 field in the update hotel page is accepting alphabets and special characters and 10 digit validation is not done. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter phone number 1 with alphabets and special characters. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept phone number 1 with alphabets and special characters. Phone number 1 should not accept alphabets and special characters and should be equal to 10 digits.It is accepted without any error. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_006 | UPDATE_HOTEL | The phone number 2 field in the update hotel page is accepting the same number which is entered in phone number 1 . (phone number 1 and phone number 2 should not be the same) | Detailed Description: The phone number 2 field in the update hotel page is accepting the same number which is entered in phone number 1. (phone number 1 and phone number 2 should not be the same) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter phone number 2 as same as phone number 1. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application can accept phone number 2 as same as phone number 1. Phone number 2 should not be as same as phone number 1.It is accepted without any acknowledgement. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_07 | UPDATE_HOTEL | The rating field in the update hotel page has no values in the drop-down. (select is registered by default) | Detailed Description: The rating field in the update hotel page has no values in the drop-down. (select is registered by default) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Click rating drop-down and check for the rating values. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is registering select in the rating drop down by default. Rating should have some values.It is accepteing the placeholder without any acknowledgement. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_08 | UPDATE_HOTEL | The e-mail field in the update hotel page is not validating the e-mail for the local-name , domain and extension. ("locat-name@domain.extension" format is not getting verified) | Detailed Description: The e-mail field in the update hotel page is not validating the e-mail for the local-name , domain and extension. ("locat-name@domain.extension" format is not getting verified) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter e-mail address without any proper e-mail format. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is accepting invalid e-mail address. E-mail should be in proper format.It is accepted without any error message. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_09 | UPDATE_HOTEL | The fax field in the update hotel page is not registering the fax number in the hotel page after registration. | Detailed Description: The fax field in the update hotel page is not getting registered and displayed in that hotel page after updating. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter fax number. 6. Click on update hotel. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is accepting valid data in all fields , but after updating hotel , it is unable to display the fax number of that particular hotel. Fax number must be available in the web page of that particular hotel. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_10 | UPDATE_HOTEL | The update hotel button in the update hotel webpage is unable to update the new details when it is clicked. | Detailed Description: The update hotel button in the update hotel webpage is unable to update the new details when it is clicked. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter valid details in all fields. 6. Click on add hotel. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is accepting valid data in all fields , but the webpage is unable to update the details of the hotel in the database. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_UPDATE_HOTEL_11 | UPDATE_HOTEL | The reset button in the update hotel webpage is unable to reset the details in the fields when it is clicked. | Detailed Description: The reset button in the update hotel webpage is unable to reset the details in the fields when it is clicked. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4.Select update hotel option from the page 5. Enter details in fields. 6. Click on reset. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to reset\clear the details in the fields when it is clicked. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Hotel List
Project ID: PRJ_HMS | Project Name : Hotel Management System
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_HOTEL_LIST_001 | HOTEL_LIST | The update button in the hotel list page is not navigating the browser to the update hotel page when it is clicked. | Detailed Description: The update button in the hotel list page is not navigating the browser to the update hotel page when it is clicked. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link. 4. Login into your account. 5. Open hotel list webpage and click update button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application cannot able to navigate the browser to the update hotel page when it is clicked. . | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_HOTEL_LIST_002 | HOTEL_LIST | The delete button in the hotel list page is not able to delete the selected hotel details from the hotel list when it is clicked. | Detailed Description: The delete button in the hotel list page is not able to delete the selected hotel details from the hotel list when it is clicked. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link. 4. Login into your account. 5. Open hotel list webpage and click delete button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application cannot able to delete the details of the selected hotel from the hotel list page when it is clicked. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
DF_HOTEL_LIST_003 | HOTEL_LIST | The logout button in the hotel list page is not able to logout of the account when it is clicked. | Detailed Description: The logout button in the hotel list page is not able to logout of the account when it is clicked. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link. 4. Login into your account. 5. Open hotel list webpage and click logout button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application cannot able to logout of the account when it is clicked. | Coding | chrome | Internal Dev | High | High | 1 | Build 1.0 | 06.10.2018 | Ijas Ahamed | Himanshu | ACT | Test Cycle 1
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.